Report

Riyadh Office Fitting-out – Ms Project Simulation (portfolio)

*Note: This is a mock project has been handmade designed by me. I hold all the rights to it. I intentionally kept this project concise for a quick read and inspection.

I fully developed and tracked this office layout project using Ms Project toolbox, covering 64 activities across seven phases, from initiation through closure. I built tas dependencies, configured working calenders ,assigned resoureces and costs , and established a schedule and cost baseline VS Actual and calculate cost and schedule variances.

The baseline covered 74 working days with a budget of SAR 325,960. The completed simulation recorded 75 working days and an actual cost of SAR 327,880, finishing on 28 January 2027—one working day later than planned and SAR 1,920 (0.59%) over budget.

During progress tracking, an extended design activity increased cost by SAR 1,920. Adjusting the sequencing of the IT design activity reduced the forecast completion delay from two working days to one, without adding planned cost.

Used earned value analysis to assess performance and reconciled a SAR 12,500 difference between actual cost and ACWP by correcting expense classification. Preserved the original baseline and exported final cost and schedule comparison reports.

Key lessons included checking dependencies before adding resources, distinguishing reporting differences from cost savings, and reviewing completion dates alongside earned value indicators.